## Slide 1
Todays Date : 26/04/2022 Project Lead : Sujil Kumar Start Date : 9/04/2022 (Sat) | AIR POLLUTION IN US
Tasks | Project Plan 2022
 | Days | 9th to 30th April 2022 |  |  |  |  |  |  |  |  |  |  |  | 
Data Research | 3 |  |  |  |  |  |  |  |  |  |  |  |  | 
Related Information Research | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
Clean Organize and Structure Data | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
Integrate Data | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
Analyze and describe Data | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
Key Finding, Conclusion & Hypothesis | 3 |  |  |  |  |  |  |  |  |  |  |  |  | 
Graphs, Conclusion, Hypothesis | 1 |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation for the presentation | 3 |  |  |  |  |  |  |  |  |  |  |  |  | 
Presentation of the results | 3 |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 2: Slide Title
Task bars (length = duration)
Milestones
To change the length of the duration bars go to Format/Size (on far right). For extreme length changes, ungroup the duration bars and scale the highlight independently.